Project Management and Risks

Development of a Mobile Application for Collaborative Trip Planning

Astana IT University

Team: Kabysheva Zukhra Yerzhankyzy, Shauzat Sayakhat Anarbekuly, Aman Yerassyl

Supervisor: Aigerim Kydyrbekova

# 1. Roles and Responsibilities

| Member | Responsibility |
| --- | --- |
| Kabysheva Zukhra Yerzhankyzy | Requirements analysis, design of the application structure, core logic, integration of components, testing and technical documentation; survey of Astana residents and user interviews. |
| Aman Yerassyl | Server side, database design and API development; participation in integration, testing and bug fixing. |
| Shauzat Sayakhat Anarbekuly | Mobile interface (screens, mockups, map) and the AI module (plan generation and AI assistant); project coordination: YouTrack, communication with the supervisor, risk management. |
| Aigerim Kydyrbekova (supervisor) | Review of key deliverables, feedback on decisions, meetings every two weeks. |

# 2. Tools and Working Process

- YouTrack (project DIP): every meaningful task has a responsible person, deadline, priority and acceptance criteria. A task is closed only when its acceptance criteria are met.

- GitHub: the main branch is the reviewed version. Each task is done in its own branch named after the task (for example, DIP-7-project-proposal), and commit messages start with the task ID ("DIP-7: Add project proposal").

- Pull requests: every change is merged through a pull request reviewed by another team member; the pull request link is added to the YouTrack task.

- Meetings: a short team call once a week; a meeting with the supervisor every two weeks.

- Tags: each pre-defense submission is tagged (pre-defense-1, pre-defense-2, final-pre-defense).

# 3. Milestones

| Milestone | Date | Deliverables |
| --- | --- | --- |
| Pre-defense 1 | 24 October 2026 | Proposal, evidence of relevance, literature review, comparisons, requirements, diagrams, mockups, verification plan, repository and YouTrack |
| Development: core | After pre-defense 1 | Flutter project, authentication, database, trip creation, AI plan generation, map |
| Pre-defense 2 | According to the university schedule | Working prototype of the core scenario |
| Development: collaboration and community | After pre-defense 2 | Invitations, voting, chat, expenses, AI assistant, feed, weather and events, offline mode |
| Testing with users | Before the final pre-defense | Tests with at least 10 users, SUS questionnaire, fixes |
| Final pre-defense | According to the university schedule | Complete application, test results, documentation |

# 4. Dependencies

- AI plan generation depends on the places database and on the API of the chosen LLM provider.

- The map and travel times depend on access to Google Maps Platform (or 2GIS as an alternative).

- Collaboration features depend on the database structure and security rules (backend).

- Mobile screens depend on the API defined by the backend; the API contract must be agreed before implementation.

- Evidence of relevance depends on the number of survey responses and interviews.

- Testing with users depends on a working prototype.

# 5. Risk Register

Probability and impact are rated Low / Medium / High.

| Risk | Prob. | Impact | Response | Owner |
| --- | --- | --- | --- | --- |
| Not enough data about places and events in Astana | Medium | High | Combine map service data with the survey of residents; start with a smaller verified set (around 150 places); events entered manually by the team for the test period | Zukhra |
| Cost of the AI API exceeds the budget | Medium | Medium | Use small models for simple tasks, send only candidate lists (short prompts), cache generated plans, set a monthly spending limit | Sayakhat |
| AI recommends non-existent places or breaks the budget | High | High | Hybrid design: places only from the database, budget calculated by code, validator with fallback plan (see AI Module Design) | Sayakhat |
| Too few survey responses or interviews | Medium | Medium | Distribute through several channels, ask each member to collect responses, extend the survey if needed and clearly label unverified assumptions | Zukhra |
| Lack of time (studies, other courses) | High | High | Prioritize Must requirements, keep Could features optional, weekly progress check in YouTrack, buffer before each pre-defense | Sayakhat |
| Maps API access or limits for Astana | Low | Medium | Test Google Maps and 2GIS early; keep place data in our own database to switch providers easily | Sayakhat |
| Real-time synchronization problems | Medium | Medium | Use Supabase Realtime; reload the saved state after reconnecting; test with several devices early | Yerassyl |
| Inappropriate content in the community feed | Medium | Low | Report button, review of reported posts, feed limited to registered users | Yerassyl |
| A team member becomes unavailable | Low | High | Shared documentation and code reviews so that every part is known by at least two members | All |